## Task List
ID | Task Name | Description | Responsible | Duration (days) | Start Date | End Date | Dependencies | Status | Priority | Notes
1 | Project Initiation | Initial project setup and paperwork | Project Manager | 10 | 2025-05-01 | 2025-05-14 |  | Not Started | High
2 | Site Preparation | Clear the site and prepare for foundation work | Site Supervisor | 15 | 2025-05-15 | 2025-06-04 | 1 | Not Started | High
3 | Foundation Work | Excavation and foundation construction | Civil Engineer | 20 | 2025-06-05 | 2025-07-02 | 2 | Not Started | High
4 | Structural Framing | Construct main building frame | Structural Engineer | 30 | 2025-07-03 | 2025-08-13 | 3 | Not Started | High
5 | Roof Installation | Install roofing system | Roofing Contractor | 15 | 2025-08-14 | 2025-09-03 | 4 | Not Started | Medium
6 | Exterior Walls | Construct exterior walls and cladding | Construction Team | 20 | 2025-08-14 | 2025-09-10 | 4 | Not Started | Medium
7 | Plumbing Rough-In | Initial plumbing installation | Plumbing Contractor | 15 | 2025-09-11 | 2025-10-01 | 4 | Not Started | Medium
8 | Electrical Rough-In | Initial electrical systems installation | Electrical Contractor | 15 | 2025-09-11 | 2025-10-01 | 4 | Not Started | Medium
9 | HVAC Installation | Install heating and cooling systems | HVAC Contractor | 20 | 2025-09-11 | 2025-10-08 | 4 | Not Started | Medium
10 | Insulation | Install building insulation | Insulation Contractor | 10 | 2025-10-09 | 2025-10-22 | 6,7,8,9 | Not Started | Medium
11 | Drywall | Install interior wall panels | Drywall Contractor | 15 | 2025-10-23 | 2025-11-12 | 10 | Not Started | Medium
12 | Interior Finishes | Paint, trim, flooring and fixtures | Interior Contractor | 25 | 2025-11-13 | 2025-12-17 | 11 | Not Started | Medium
13 | Final Plumbing | Complete plumbing fixtures and connections | Plumbing Contractor | 10 | 2025-12-18 | 2025-12-31 | 12 | Not Started | Medium
14 | Final Electrical | Complete electrical fixtures and connections | Electrical Contractor | 10 | 2025-12-18 | 2025-12-31 | 12 | Not Started | Medium
15 | Site Cleanup | Final site cleanup and preparation | Site Supervisor | 5 | 2026-01-01 | 2026-01-07 | 13,14 | Not Started | Low
16 | Final Inspection | Regulatory inspections and approvals | Project Manager | 5 | 2026-01-08 | 2026-01-14 | 15 | Not Started | High
17 | Project Handover | Complete documentation and client handover | Project Manager | 3 | 2026-01-15 | 2026-01-19 | 16 | Not Started | High

## Gantt Chart
ID | Task Name | Start Date | End Date | Duration (days) | Week 1 05/01 | Week 2 05/08 | Week 3 05/15 | Week 4 05/22 | Week 5 05/29 | Week 6 06/05 | Week 7 06/12 | Week 8 06/19 | Week 9 06/26 | Week 10 07/03 | Week 11 07/10 | Week 12 07/17 | Week 13 07/24 | Week 14 07/31 | Week 15 08/07 | Week 16 08/14 | Week 17 08/21 | Week 18 08/28 | Week 19 09/04 | Week 20 09/11 | Week 21 09/18 | Week 22 09/25 | Week 23 10/02 | Week 24 10/09 | Week 25 10/16 | Week 26 10/23 | Week 27 10/30 | Week 28 11/06 | Week 29 11/13 | Week 30 11/20 | Week 31 11/27 | Week 32 12/04 | Week 33 12/11 | Week 34 12/18 | Week 35 12/25 | Week 36 01/01 | Week 37 01/08 | Week 38 01/15
1 | Project Initiation | 2025-05-01 | 2025-05-14 | 10
2 | Site Preparation | 2025-05-15 | 2025-06-04 | 15
3 | Foundation Work | 2025-06-05 | 2025-07-02 | 20
4 | Structural Framing | 2025-07-03 | 2025-08-13 | 30
5 | Roof Installation | 2025-08-14 | 2025-09-03 | 15
6 | Exterior Walls | 2025-08-14 | 2025-09-10 | 20
7 | Plumbing Rough-In | 2025-09-11 | 2025-10-01 | 15
8 | Electrical Rough-In | 2025-09-11 | 2025-10-01 | 15
9 | HVAC Installation | 2025-09-11 | 2025-10-08 | 20
10 | Insulation | 2025-10-09 | 2025-10-22 | 10
11 | Drywall | 2025-10-23 | 2025-11-12 | 15
12 | Interior Finishes | 2025-11-13 | 2025-12-17 | 25
13 | Final Plumbing | 2025-12-18 | 2025-12-31 | 10
14 | Final Electrical | 2025-12-18 | 2025-12-31 | 10
15 | Site Cleanup | 2026-01-01 | 2026-01-07 | 5
16 | Final Inspection | 2026-01-08 | 2026-01-14 | 5
17 | Project Handover | 2026-01-15 | 2026-01-19 | 3

## Milestones
ID | Milestone Name | Target Date | Responsible | Associated Tasks | Status | Notes
M1 | Project Start | 2025-05-01 | Project Manager | 1 | Not Started
M2 | Foundation Complete | 2025-07-02 | Civil Engineer | 3 | Not Started
M3 | Structure Complete | 2025-08-13 | Structural Engineer | 4 | Not Started
M4 | Building Enclosed | 2025-09-10 | Construction Team | 5,6 | Not Started
M5 | MEP Rough-in Complete | 2025-10-08 | MEP Coordinator | 7,8,9 | Not Started
M6 | Interior Finishes Complete | 2025-12-17 | Interior Contractor | 12 | Not Started
M7 | Final Inspections | 2026-01-14 | Project Manager | 16 | Not Started
M8 | Project Completion | 2026-01-19 | Project Manager | 17 | Not Started

## Constraints
ID | Constraint Type | Description | Impact | Affected Tasks | Mitigation Plan | Status | Responsible
C1 | Weather | Winter conditions may delay exterior work | Schedule delay | 5,6 | Schedule exterior work in warmer months, prepare contingency plan | Active | Project Manager
C2 | Regulatory | Building permit approval process | Cannot start construction without permits | 2,3 | Submit applications early, follow up regularly | Active | Permit Coordinator
C3 | Resource | Limited skilled labor availability | Potential delays in specialized work | 7,8,9 | Pre-book contractors, consider alternative sourcing | Active | Resource Manager
C4 | Budget | Material cost fluctuations | Budget overruns | All | Secure price commitments early, include contingency budget | Active | Financial Manager
C5 | Site | Limited site access for deliveries | Logistics complications | All | Create detailed delivery schedule, coordinate with neighbors | Active | Site Supervisor
C6 | Technical | Complex foundation requirements | Additional engineering required | 3 | Early engagement with geotechnical experts | Active | Civil Engineer
C7 | Environmental | Noise restrictions during certain hours | Limited working hours | All | Schedule noisy work during permitted hours, notify community | Active | Site Supervisor

## Logistic Phasing
Phase | Start Date | End Date | Description | Tasks Involved | Resources Required | Site Access Points | Storage Areas | Special Requirements
Phase 1 | 2025-05-01 | 2025-07-02 | Site Preparation & Foundation | 1,2,3 | Excavators, Concrete trucks, Laborers | Main entrance | North corner of site | Temporary fencing, Silt control
Phase 2 | 2025-07-03 | 2025-09-10 | Structure & Envelope | 4,5,6 | Crane, Delivery trucks, Framing team | Main and east entrances | East side of building | Staging area for materials, Tower crane setup
Phase 3 | 2025-09-11 | 2025-10-22 | MEP Rough-In & Insulation | 7,8,9,10 | Specialized contractors, Material deliveries | All entrances | Interior of building | Secure storage for equipment, Temporary power
Phase 4 | 2025-10-23 | 2025-12-31 | Interior Finishes & MEP Completion | 11,12,13,14 | Finish contractors, Fixtures deliveries | Main entrance only | Interior secured rooms | Climate control active, Dust control measures
Phase 5 | 2026-01-01 | 2026-01-19 | Completion & Handover | 15,16,17 | Cleaning crews, Inspection teams | Restricted access | Minimal on-site storage | Furniture deliveries, Systems testing