## Submittal Log
CONSTRUCTION SUBMITTAL LOG
Project Name: | ENTER PROJECT NAME |  |  |  |  | Project No.: | ENTER PROJECT NO.
Contractor: | ENTER CONTRACTOR NAME |  |  |  |  | Updated: | 04/20/2025
Submittal No. | Spec Section | Description | Submittal Type | Subcontractor | Required Date | Date Received | Status | Returned Date | Remarks
001 | 03 30 00 | Concrete Mix Design | Product Data | ABC Concrete | 05/01/2025 | 04/15/2025 | Approved | 04/20/2025
002 | 04 20 00 | Masonry Units | Samples | XYZ Masonry | 05/15/2025 | 04/22/2025 | Approved as Noted | 04/27/2025 | Resubmit color samples
003 | 05 12 00 | Structural Steel | Shop Drawings | Steel Fabricators Inc. | 05/30/2025 |  | Pending
004 | 07 21 00 | Insulation | Product Data | Insulation Co. | 06/15/2025 |  | Pending
005 | 08 11 13 | Hollow Metal Doors | Shop Drawings | Door Suppliers LLC | 06/30/2025 |  | Pending

## Package Template
SUBMITTAL PACKAGE COVER SHEET
Project Name: | ENTER PROJECT NAME |  | Project No.: | ENTER PROJECT NO.
Contractor: | ENTER CONTRACTOR NAME |  | Date: | 04/20/2025
SUBMITTAL PACKAGE INFORMATION
Package No.: |  |  | Specification Section(s):
Package Description:
Submitted By: |  |  | Title:
SUBMITTAL ITEMS INCLUDED IN THIS PACKAGE
Item No. | Description | Type | No. of Copies | Spec Reference | Remarks
1
2
3
4
5
REVIEW ACTION
□ APPROVED | □ APPROVED AS NOTED | □ REVISE AND RESUBMIT | □ REJECTED | □ FOR INFORMATION ONLY
Comments:
Reviewed By: |  |  | Date:

## Item Form
SUBMITTAL ITEM FORM
Project Name: | ENTER PROJECT NAME |  | Project No.: | ENTER PROJECT NO.
Contractor: | ENTER CONTRACTOR NAME |  | Date: | 04/20/2025
SUBMITTAL INFORMATION
Submittal No.: |  |  | Spec Section:
Description:
Submittal Type:
□ Product Data | □ Shop Drawings | □ Samples | □ Quality Control | □ Other:___________
Subcontractor:
Manufacturer:
Supplier:
CONTRACTOR REVIEW
□ Approved | □ Approved as Noted | □ Revise and Resubmit | □ Rejected
Comments:
Reviewer: |  |  | Date:
ARCHITECT/ENGINEER REVIEW
□ Approved | □ Approved as Noted | □ Revise and Resubmit | □ Rejected | □ For Information Only
Comments:
Reviewer: |  |  | Date:

## Instructions
CONSTRUCTION SUBMITTAL TRACKING WORKBOOK - INSTRUCTIONS
Overview:
This workbook contains templates for tracking construction submittals, creating submittal packages, and documenting individual submittal items.
Sheets Included:
1. Submittal Log - For tracking all project submittals
2. Package Template - Template for creating submittal package cover sheets
3. Item Form - Template for individual submittal item documentation
How to Use:
Submittal Log:
- Enter project information at the top
- Assign sequential submittal numbers
- Enter specification section references
- Track status and dates for each submittal
- Update the log regularly as submittals are processed
Package Template:
- Complete this form when bundling multiple related submittals
- Assign a package number
- List all submittal items included in the package
- Attach this as a cover sheet to the physical submittal package
Item Form:
- Complete this form for each individual submittal item
- Document contractor review before submission
- Record architect/engineer review after return
- Include with the actual submittal materials
Submittal Status Options:
- Pending: Not yet received from subcontractor/supplier
- In Review: Received but not yet reviewed
- Approved: Reviewed and accepted without changes
- Approved as Noted: Approved with minor changes noted
- Revise and Resubmit: Requires correction and resubmission
- Rejected: Not acceptable, must be resubmitted
- For Information Only: Provided for reference, no approval required
Tips:
- Make a copy of the template sheets as needed
- Maintain consistent submittal numbering
- Use clear, descriptive titles for submittals
- Track resubmittals with the original number plus a revision suffix (e.g., 001-R1)
- Set up automatic conditional formatting to highlight late or overdue submittals